## Sheet1
Formal User Story/Description | Priority | Complexity
As a user, I want to be able to search for a procedure by code so I can find the correct procedure. | 10 | 1 | sprint 1
As a user, I want to be able to search for a procedure by description so I can find the correct procedure. | 7 | 2 | sprint 1 | Story Point (Based off user story 1)
As a user, I want to be able to sort hospital results based on my provided location so I can find the closest hospital. | 9 | 4 | sprint 1 | Person | Hour for 1 Story Point
As a user, I want to sort results based on price of the procedure, so I can determine the cheapest hospital | 9 | 1 | sprint 1 | Caoilainn McCrory | 4
As a disabled user, I want to be able to use my screen reader to be able to read the results. | 8 | 1 | sprint 1 | Daniel Sewerynski | 2
As a user, I want to see the results of my search displayed on a map to make it easier to determine where potential hospitals for my procedure are located | 5 | 4 | Completed in sprint 1 | Feng Qu | 5
As a user, I want to be able to restrict the results by price so that I can exclude hospitals that are out of my price range. | 6 | 1 | Completed in sprint 1 | Melvin Abraham | 4
As a user, I want to be able to set how far I am willing to travel, I can exclude hospitals that are too far away. | 6 | 4 | Completed in sprint 1 | Naqash Nadeem | 5
As the service provider, I want to be able to update the dataset so that the results are as up to date as possible. | 4 | 6 |  | Robert Hampton | 3
As a purchaser, I want users to be recommended hospitals based on price, distance and user feedback so they have better search results | 4 | 6
As a purchaser, I want machine learning to be incorporated into search results so users can search for procedures more efficiently. | 2 | 9
As a disabled user, I want to be able to change the text size so that I can read better. | 1 | 2
As a disabled user, I want to be able to change the text color and background so that I can read it better. | 1 | 2