## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I want to be able to search for a procedure by code so I can find the correct procedure. | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
As a user, I want to be able to search for a procedure by description so I can find the correct procedure. | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
As a user, I want to be able to sort hospital results based on my provided location so I can find the closest hospital. | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
As a user, I want to sort results based on price of the procedure, so I can determine the cheapest hospital | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
As a disabled user, I want to be able to use my screen reader to be able to read the results. | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I want to be able to search for a procedure by code so I can find the correct procedure. | 3
Create SQL statement |  | Caoilainn | Finished | 0.5 |  | 0.5
Store data appropriately |  | Feng + Naqash | Finished | 1 |  | 1
Display data |  | Robert + Melvin | Finished | 0.5 |  | 1
Store hospital location data |  | Daniel | Finished
As a user, I want to be able to search for a procedure by description so I can find the correct procedure. | 3
Create SQL statement |  | Caoilainn | Finished | 0.25 |  | 0.5
Display Data |  | Robert+ Melvin | Finished | 0.5 |  | 1
Drop down options for type of operations |  | Feng + Naqash | Finished | 1 |  | 1
As a user, I want to be able to sort hospital results based on my provided location so I can find the closest hospital. | 5
Sort the result of the query by Location |  | Caoilainn + Melvin + Robert + Daniel | Finished | 8 |  |  | 7 | 1
Display data on map |  | Robert + Daniel | Finished | 10 |  |  | 5 | 5
As a user, I want to sort results based on price of the procedure, so I can determine the cheapest hospital | 2
Sort the result of the query by Price |  | Feng + Naqash | Finished | 8 |  |  | 6 | 2
Display data on map |  | Robert + Daniel +Caoilainn | Finished | 10 |  |  | 5 | 5
Range slider for price |  | Feng + Naqash | Finished | 3 |  |  | 3
As a disabled user, I want to be able to use my screen reader to be able to read the results. | 3
Reconfigure Html structure to aid screen reader |  | Melvin | Finished | 2 |  |  | 1 | 1
Setup | 5
Github |  | Melvin | Finished | 0.5 | 0.5
Setup azure |  | Daniel + Caoilainn | Finished | 1 | 1 | 1
Create tables |  | Melvin | Finished | 0.5 | 0.5
Setup MySql |  | Caoilainn + Daniel | Finished | 1 | 3
Java connection to database |  | Robert | Finished | 1 |  | 1
Populate Database |  | Melvin + Caoilainn + Daniel | Finished | 2 | 1 | 1
Website Frontend |  | Feng + Naqash+ Robert | Finished | 4 | 3 | 1
TOTAL |  |  |  | 44.75 | 9 | 9 | 27 | 14 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.