## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user I want to only see relevant information so that I don't get overwhelmed with information | 1 | Melvin | Finished | 4 | 4
Remove Address |  |  | Finished |  | 1
Remove ZipCode |  |  | Finished |  | 1
Remove State |  |  | Finished |  | 2
As a user I want to see where the hospital is on the map clearly so I don't get confused between other locations on the map | 1 | Robert |  | 4 | 1
Change map layer used |  |  | Not required
Change map markers |  |  | Finished |  | 1
Task
Task
As a user I want to see specific information of the hospital when I click on their icon on the map so that it is clear which icon represents which hospital | 3 | Robert, Melvin |  | 12
Create custom map marker/modal |  |  |  | 0.5 | 0.5
Add funtion to make modal pop up on marker click |  |  |  | 0.5 | 0.5
Display appropriate info on modal |  |  |  | 1 |  | 1
Task
As a user I want to click on a hospital suggestion and see it on the map clearly so that I can see where the hospital is located | 3 | Caoilainn |  | 12
Add 'Find On Map' button
Add function to display chosen hospital on map
Task
Task
As a user I would like the website to give me an auto complete feature to help me find my operation quicker | 2 | Daniel |  | 8
Task
Task
Task
Task
As a user I would like to be able to see if I searched for an operation that does not exist so that I can readjust my search | 1 | Naqash, Feng |  | 4 | 4
Task
Task
Task
Task
As a programmer I want to be able to differentiate the operation title from the code number so I can manipulate them individually without dependencies | 3 | Daniel |  | 12
Normalize database |  |  |  |  | 3
Change index user interface |  |  |  |  | 1
Update stored procedure |  |  |  |  | 2
As a user I want to be able to return to the home page to do a new search | 1 | Melvin |  | 1
Add back button |  |  | Finished | 1 |  | 1
TOTAL |  |  |  | 59 | 17 | 1 | 0 | 0 | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.