## Sheet1
Formal User Story/Description | Priority | Complexity
As a user, I want to be able to search for a procedure by code so I can find the correct procedure. | 10 | 1 | sprint 1
As a user, I want to be able to search for a procedure by description so I can find the correct procedure. | 7 | 2 | sprint 1 |  | Story Point (Based off user story 1)
As a user, I want to be able to sort hospital results based on my provided location so I can find the closest hospital. | 9 | 4 | sprint 1 |  | Person | Hour for 1 Story Point
As a user, I want to sort results based on price of the procedure, so I can determine the cheapest hospital | 9 | 1 | sprint 1 |  | Caoilainn McCrory | 4
As a disabled user, I want to be able to use my screen reader to be able to read the results. | 8 | 1 | sprint 1 |  | Daniel Sewerynski | 2
As a user, I want to see the results of my search displayed on a map to make it easier to determine where potential hospitals for my procedure are located | 5 | 4 | Completed in sprint 1 |  | Feng Qu | 5
As a user, I want to be able to restrict the results by price so that I can exclude hospitals that are out of my price range. | 6 | 1 | Completed in sprint 1 |  | Melvin Abraham | 4
As a user, I want to be able to set how far I am willing to travel, I can exclude hospitals that are too far away. | 6 | 4 | Completed in sprint 1 |  | Naqash Nadeem | 5
As the service provider, I want to be able to update the dataset so that the results are as up to date as possible. | 2 | 6 | Not attempted | Out of scope | Robert Hampton | 3
As a purchaser, I want users to be recommended hospitals based on price, distance and user feedback so they have better search results | 2 | 6 | Not attempted | Out of scope
As a purchaser, I want machine learning to be incorporated into search results so users can search for procedures more efficiently. | 1 | 9 | Not attempted | Out of scope
As a disabled user, I want to be able to change the text size so that I can read better. | 1 | 2 | Not attempted | Not considered priority
As a disabled user, I want to be able to change the text color and background so that I can read it better. | 1 | 2 | Not attempted | Not considered priority
As a user I want to only see relevant information so that I don't get overwhelmed with information | 10 | 1 | sprint 2
As a user I want to see specific information of the hospital when I click on their icon on the map so that it is clear which icon represents which hospital | 9 | 3 | sprint 2
As a user I want to see where the hospital is on the map clearly so I don't get confused between other locations on the map | 8 | 1 | sprint 2
As a programmer I want to be able to differentiate the operation title from the code number so I can manipulate them individually without dependencies | 8 | 3 | sprint 2
As a user I want to click on a hospital suggestion and see it on the map clearly so that I can see where the hospital is located | 7 | 3 | sprint 2
As a user I would like to be able to see if I searched for an operation that does not exist so that I can readjust my search | 6 | 1 | sprint 2
As a user I would like the website to give me an auto complete feature to help me find my operation quicker | 5 | 2 | sprint 2
As a user I want to be able to return to the home page to do a new search | 2 | 1 | sprint 2